## Project Risk Log
GNAO Risk Register C - GNAO - 002
Part I. Risk Identification | [5 empty] | Part II. Risk Analysis for Existing Controls |  |  | Part III. Risk Response
Name | Project Risk Category | Risk Description (ignoring controls) [use: if, because, then] | Impact 1-5 (ignoring controls) | Likelihood 1-5 (ignoring controls) | Total Risk Score Low = 1 - 8 Med = 9 - 16 High = 17 - 25 | What Controls (if any) are currently in place? | Control Effectiveness 1-5 | Residual Risk Score Low = 1 - 8 Med = 9 - 16 High = 17 - 25 | Control or Risk Mitigation Strategy | Control effectiveness based on mitigation strategy 1-5 | Residual Mitigated Risk Low = 1 - 8 Med = 9 - 16 High = 17 - 25 | Contingency Plan | Cost of contingency plan | Owner | Review Due Date | Status
Late production of Science Cases and CONOPS | Technical | If the Science Cases work is not completed early then the GNAO/RTC requirements set will be incomplete, possibly resulting in an inadequate design impacting the schedule. | 5 | 3 | 15 | The Science Team was identified early and the science cases are nearing completion. | 1 | 0.15
Staffing | Resources | If the two open positions on the GNAO/RTC Team (Senior Systems Engineer, Senior Project Manager) are not filled in a timely manner then significant schedule slips might occur due to lack of key staff. | 5 | 4 | 20 | PM has been filled, SE is in process | 2 | 5
Internal resource shortage | Resources | If the current team is allocated to other projects then the project may fall behind schedule | 4 | 5 | 20 | The project has been made the highest priority at the Observatory (even above operations); we are still leaving "Control Effectiveness" set to 3 until we see the practical effect of this highest priority mandate | 3 | 10 | More assertively enforce highest priority mandate
Late ASM and GNAOI interface / integration requirements (since they are outside the scope) | Technical | If the requirements are not developed and the interfaces can not be completed the project completion will not be met. | 3 | 3 | 9 | GNAO/RTC is no longer depenndent on the ASM and GNAOI is in process | 2 | 2.25 | Bring GSAOI up from south to use in place of GNAOI temporarily
Procurements | Schedule | If procurements are not comleted in a timely manner the scheulde will slip. | 5 | 4 | 20 | A phased procurement strategy has been developed, in conversation with long-lead-time vendors, and will implementedd as we conclude CoD; this is still a relatively likely risk, none-the-less, given the time frame of the project | 3 | 10 | Explore ways to expedite the procurement process and possible alternate vendors
Vendor Delays | Technical | Interface management risk - if the strategy to procure major (non off-the-shelf) subassemblies from different vendors is delayed this may impact schedule and budget. | 3 | 3 | 9 | We have been in conversation with potential vendors; this is still a relatively likely risk, none-the-less, given the time frame of the project | 3 | 4.5
Requirements | Technical | GNAO/RTC design needs to be compatible with the yet to be specified ASM. The opto-mechanical design of the MCAO AOB has to be built in such a way that replacing DM0 with M2 is possible and if not will impact budget and schedule. | 3 | 4 | 12 | Specify the ASM early; this is beginning, but needs to be progressed | 4 | 9 | Infer ASM-related requirements on GNAO-RTC given internal AO expertise and access to external experts
Legacy hardware interfaces for GeMS RTC | Schedule | Insufficient information on legacy hardware to implement interfaces to new RTC may impact schedule. | 4 | 3 | 12 | Begin evaluating interfaces early | 3 | 6

## Closed risks
MOVE CLOSED RISKS INTO THIS TAB
Part I. Risk Identification | [5 empty] | Part II. Risk Analysis for Existing Controls |  |  | Part III. Risk Response
Name | Project Risk Category | Risk Description (ignoring controls) | Impact 1-5 (ignoring controls) | Likelihood 1-5 (ignoring controls) | Total Risk Score Low = 1 - 8 Med = 9 - 16 High = 17 - 25 | What Controls (if any) are currently in place? | Control Effectiveness 1-5 | Residual Risk Score Low = 1 - 8 Med = 9 - 16 High = 17 - 25 | Control or Risk Mitigation Strategy | Control effectiveness based on mitigation strategy 1-5 | Residual Mitigated Risk Low = 1 - 8 Med = 9 - 16 High = 17 - 25 | Contingency Plan | Cost of contingency plan | Owner | Review Due Date | Status

## Grading Criteria
NOTE: Each project owns customizing this worksheet to criteria that makes sense for their project.
Impact - Scale
Impact Criteria | 1 | 2 | 3 | 4 | 5
Technology Risk | Known technology |  | Known technical foundation |  | State of the art technology
Resource Competency / availability | Competency in-house |  | Some in-house / some known external |  | Minimal to no in-house knowledge
Strategic / Telescope interruption or Competitive Disadvantage | Low Severity (Manual process could recover) |  | Medium Severity |  | High Severity or Business Stop
Schedule | Schedule well understood |  | Schedule has some unknowns |  | Schedule is not well understood
Financial loss | <=$250K |  | $250k - $5M |  | >=$5M
Scope | Scope well understood; no change requests submitted |  | Scope gaps exist in non-critical areas. Some change requests submitted or expected | N/A | Scope not well defined. Change requests inevitable
Likelihood - Scale
Likelihood Criteria | 1 | 2 | 3 | 4 | 5
Probability | 0% | 25% | 50% | 75% | 100%
Descriptive | Remote |  | Probably |  | Certain
Controls Effectiveness - Scale
| 1 | 2 | 3 | 4 | 5
Weight for calc purposes, DO NOT CHANGE | 99% | 75% | 50% | 25% | 1%
Descriptive | Existing - Sufficient |  | Existing - Non Sufficient |  | Non-Existent